## Model 5.2 - ModelRisk
Model 5.2 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Routledge
Simulation uses ModelRisk - visit www.vosesoftware.com to download free trial license of the ModelRisk tool
Net Present Value Risk Model with correlation of risk model cost inputs
Risk Model Inputs |  |  |  |  | Apportionment | [11 empty] | Costs and benefits simulated by year
| Cost (£k) |  |  |  | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | Check
| Min | Mode | Max | Simulated | [25 empty] | Correlation
Land for new factory |  | 2000 |  | 2000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 |  | Eng team | Design | Build con | Equip con | Handover | Proj Man | Simulation
In-house engineering team | 450 | 700 | 1000 | #NAME? | 0 | 0.4 | 0.4 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Eng team | 1 | 0.8 | 0.7 | 0.7 | 0 | 0.8 | #NAME?
Design contract | 1600 | 2300 | 3000 | #NAME? | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Design | 0.8 | 1 | 0.8 | 0.8 | 0 | 0.8 | #NAME?
Building contract | 20000 | 28000 | 40000 | #NAME? | 0 | 0.25 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Build con | 0.7 | 0.8 | 1 | 0.7 | 0 | 0.7 | #NAME?
Equipment contract | 34000 | 40000 | 46000 | #NAME? | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Equip con | 0.7 | 0.8 | 0.7 | 1 | 0 | 0.7 | #NAME?
Factory handover | 1400 | 1600 | 2000 | #NAME? | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Handover | 0 | 0 | 0 | 0 | 1 | 0.3 | #NAME?
Project Management | 3000 | 3500 | 4200 | #NAME? | 0 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | Proj Man | 0.8 | 0.8 | 0.7 | 0.7 | 0.3 | 1 | #NAME?
Benefits (£k)
| Min | Mode | Max | Simulated
Sale of old site | 1500 | 2000 | 2500 | #NAME? | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Annual profit increase | 18000 |  | 22000 | #NAME? | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
NPV Results calculation | [16 empty] | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Project cost (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Project benefits value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
In-year Net value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Discount Rate | 6%
Discount factor (using D = 6%) | [16 empty] | 1 | 0.97129 | 0.91631 | 0.86444 | 0.81551 | 0.76935 | 0.7258 | 0.68472 | 0.64596 | 0.6094 | 0.5749
In-year Net Present Value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Cumulative NPV (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Notes
1. The cost and benefits amortisation inputs are in the hidden colums F - R. Note that, given that these values are fixed, the effect of schedule risk is not included in the model.
2. Discount factors are calculated to correspond to mid-year values
3. Risk estimating inputs are colour coded Optimistic, Mode and Pessimistic
4. Brown font represents the Monte Carlo simulation input cells
5. Purple font represents the Monte Carlo simulation output (at Cell AE30)
6. The Check cells verify that model the is internally coherent. Check cells fill becomes red where this is not the case.
7. This example is identical to Model 5.1 but with the addition of correlation inputs for cost risk.