## Model 6.6 - ModelRisk
NPV Risk Model 6.6 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Routledge
Simulation uses ModelRisk - visit www.vosesoftware.com to download free trial license of the ModelRisk tool
Space Industry Units Production - Production of 2 Off units
Estimates |  | Notes
Base Estimates
No. of units required | 2 | s = number of successfully manufactured units
Time to make 1 Off unit (days) | 30 | d = duration for manufacture of one unt
Cost of making 1 Off Unit (£k) | 150 | c = cost per unit
Remakes risk
Success probability for each unit | 50% | p = probability of successful manufacture of each unit
Number of remakes | #NAME? | No. of remakes = NegBin(s,p)
Base + Risk
Production schedule (days) | #NAME? | Risk Model output = t (s + NegBin(s,p))
Production Cost (£k) | #NAME? | Risk Model output = c (s + NegBin(s,p))

## RiskSerializationData (hidden)
1 | 0
0
#REF! | TRUE | 0 | 1 | GF1_rK0qDwEADADVAAwjACYAOQBZAG0AbgB6AIYArwDRAMsAKgD//wAAAAAAAQQAAAAABSMsIyMwAAAAARpBbm51YWwgc2FsYXJpZXMgY29zdCAowqNrKQEAAQEQAAIAAQpTdGF0aXN0aWNzAwEBAP8BAQEBAQABAQEAAgABAQEBAQABAQEAAgABigACIQAaQW5udWFsIHNhbGFyaWVzIGNvc3QgKMKjaykAAC8BAgACALcAwQABAQIBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQABAQEA | 1 | 0 | 0 | >75% | <25% | >90% | #REF! | 1 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 15680 | 7345 | 13120 | 100
FALSE | 15680 | 7345 | 13120 | 500
FALSE | 15680 | 7345 | 13120 | 1000
FALSE | 15680 | 7345 | 13120 | 1500
FALSE | 15680 | 7345 | 13120 | 2000
0
0 | FALSE | FALSE | 10 | 0.95 | 1